AFYALINK Project Blueprint and Engineering Workplan A secure platform linking healthcare professionals, regulatory bodies, and employing facilities Prepared for: Afyalink Founding / Engineering Team Version: 1.0 Date: May 2026

Document purpose This document converts the Afyalink idea into a buildable product and engineering plan. It defines the business workflow, platform modules, recommended frameworks, database structure, security design, implementation roadmap, and a detailed Milestone 1 delivery plan.

Important security note The platform can block downloads, disable obvious browser actions, use private file delivery, and apply visible watermarks. However, no web platform can technically guarantee that screenshots or external phone photos are impossible. Afyalink should combine technical controls, watermarking, audit logs, contracts, and legal terms.

# Contents

1. Executive Summary

2. Product Vision and Business Model

3. Regulatory and Compliance Foundation

4. Stakeholders, User Roles, and Permissions

5. Product Modules and User Journeys

6. Engineering Architecture

7. Recommended Frameworks and Technology Stack

8. Security, Privacy, and Document Protection

9. Data Model and Core Database Tables

10. API and Integration Design

11. Verification, Interview, and Recommendation Workflows

12. Milestone Roadmap

13. Milestone 1 Detailed Build Plan

14. Delivery Team, Testing, Risks, and References

# 1. Executive Summary

Afyalink is designed as a trust infrastructure layer for healthcare staffing. The platform receives applications from healthcare professionals, captures their credentials, verifies those credentials with relevant regulatory bodies, interviews the professionals at a fee, and publishes approved candidates to paying healthcare facilities in a controlled read-only portal.

The platform’s core value is not just recruitment. It is verified trust: facility managers should be able to view a candidate’s license status, credential evidence, interview marks, Afyalink recommendation, and availability without downloading or misusing sensitive records.

| Strategic Area | Afyalink Position |
| --- | --- |
| Market role | Credential verification, professional screening, interview scoring, and healthcare facility matching. |
| Main customers | Healthcare facilities, clinics, hospitals, pharmacies, laboratories, NGOs, and health programs needing trusted professionals. |
| Main supply users | Healthcare professionals seeking verified placement visibility and improved employability. |
| Revenue streams | Professional application/interview fees, facility subscriptions, appointment booking fees, recommendation packages, and premium verification reports. |
| Engineering focus | Security, private document handling, auditability, regulatory workflow tracking, reliable payments, and scalable portal architecture. |
| MVP goal | Launch professional onboarding, credential intake, consent capture, payment confirmation, and admin review before building facility access. |

Recommended build philosophy Build Afyalink first as a secure modular monolith with clean internal modules. This keeps delivery fast while preserving a path to future microservices if traffic, integrations, or team size grows.

# 2. Product Vision and Business Model

## 2.1 Vision Statement

To become the trusted verification and staffing bridge between healthcare professionals, healthcare regulatory bodies, and facilities that employ clinical talent.

## 2.2 Core Objectives

Trust: Help facilities make safer hiring decisions using verified credentials and structured interview results.

Speed: Reduce the time facilities spend checking documents manually.

Compliance: Create a documented, auditable process for professional verification and facility access.

Professional visibility: Give qualified professionals a credible verified profile that increases placement opportunities.

Data protection: Protect personal and professional records using private storage, consent, role-based access, and audit logs.

## 2.3 Revenue Model

| Revenue Item | Who Pays | Description | MVP Priority |
| --- | --- | --- | --- |
| Application / interview fee | Professional | Fee paid before Afyalink reviews credentials and conducts screening interview. | High |
| Facility subscription | Facility | Recurring fee to access verified candidates and request recommendations. | Medium |
| Candidate recommendation package | Facility | Afyalink prepares a shortlist and recommendation for a role or department. | Medium |
| Appointment booking / consultation | Facility | Facility books a meeting with Afyalink to discuss staffing needs. | Medium |
| Premium verification report | Facility or partner | Detailed verification certificate and risk notes for selected candidates. | Later |
| Enterprise staffing contract | Facility or health program | Bulk screening and placement support for large hiring needs. | Later |

# 3. Regulatory and Compliance Foundation

Afyalink must treat healthcare credential verification as a regulated, high-trust workflow. The platform should not present itself as replacing regulatory bodies. Its role should be to collect professional consent, verify submitted details with the relevant authority, record the verification evidence, and present the verified status to authorized facilities.

## 3.1 Regulatory Context

Kenya Health Professions Oversight Authority provides oversight in healthcare services, training, registration, and licensing of health professionals, and coordinates joint health inspections.

Kenya Ministry of Health lists several regulatory bodies and councils, including the Clinical Officers Council, KMPDC, Nursing Council of Kenya, Occupational Therapy Council, Physiotherapy Council, and Public Health Officers and Technicians Council.

Profession-specific councils provide registration, licensing, retention, and in some cases public license-status search functions.

Afyalink will process personal data, credentials, identification documents, contact details, employment history, and interview results. This requires a data protection-first design.

## 3.2 Priority Regulatory Bodies to Support First

| Profession Category | Likely Regulatory Body / Source | Verification Data Needed |
| --- | --- | --- |
| Medical / dental practitioners | Kenya Medical Practitioners and Dentists Council (KMPDC) | Name, registration/license number, license status, expiry date, facility license where relevant. |
| Nurses and midwives | Nursing Council of Kenya (NCK) | NCK license number/status, retention/renewal status, expiry date. |
| Clinical officers | Clinical Officers Council (COC) | Retention register status, license number, practice license status. |
| Pharmacists / pharmaceutical technologists | Pharmacy and Poisons Board (PPB) | Professional registration, license status, and pharmacy-related compliance where applicable. |
| Public health officers / technicians | Public Health Officers and Technicians Council | Registration, license/retention status, practice category. |
| Physiotherapists / occupational therapists / nutritionists / lab professionals | Relevant councils and boards as supported in phased rollout | Profession-specific registration, validity, and scope of practice. |

## 3.3 Compliance Actions Required

Consent capture: Every professional must consent to credential verification, document storage, interview scoring, and controlled sharing with registered facilities.

Data protection registration: Assess Afyalink’s obligation to register with the Office of the Data Protection Commissioner as a data controller and/or processor.

Data Processing Agreements: Create facility terms restricting download, reuse, copying, publishing, or hiring misuse of candidate information.

Retention rules: Define how long rejected, expired, withdrawn, and inactive professional records are kept.

Auditability: Log every sensitive view, status change, credential verification action, interview score update, payment callback, and facility access event.

Manual override controls: Admins must not be able to secretly alter verification or interview results without traceable audit entries.

# 4. Stakeholders, User Roles, and Permissions

Afyalink must be role-driven from day one. Access control should be designed before database tables and screens are finalized because the platform handles sensitive professional and employment records.

| Role | Primary Capabilities | Key Restrictions |
| --- | --- | --- |
| Professional | Register, complete profile, upload credentials, give consent, pay fee, track application status, update expired documents. | Cannot view other professionals, facility accounts, internal notes, or verification evidence meant only for Afyalink. |
| Afyalink Super Admin | Manage users, settings, roles, billing configuration, document types, facility accounts, and audit reports. | Should use MFA; actions are fully audited. |
| Verification Officer | Review documents, contact regulatory bodies, record verification evidence, request replacements. | Cannot edit interview score after submission unless granted special permission. |
| Interviewer | View assigned candidates, conduct interview, submit structured marks and comments. | Cannot change credential verification results. |
| Facility Admin | Manage facility profile, users, subscription, appointments, shortlist requests, and paid access. | Cannot download candidate documents or see unpublished candidates. |
| Facility Viewer | View approved candidates in read-only mode with watermark and audit trail. | Cannot manage payments, export data, or access raw documents beyond authorized viewer. |
| Support Agent | Handle support tickets, resend emails, help users with account issues. | Cannot see sensitive documents unless specifically elevated. |

## 4.1 Permissions Matrix

| Capability | Professional | Verification Officer | Interviewer | Facility Admin | Super Admin |
| --- | --- | --- | --- | --- | --- |
| Create / edit own profile | Yes | No | No | No | Yes |
| Upload credentials | Yes | No | No | No | Yes |
| View raw documents | Own only | Assigned | Limited | No / controlled | Yes |
| Verify credentials | No | Yes | No | No | Yes |
| Submit interview scores | No | No | Yes | No | Yes |
| View approved candidates | Own status only | Yes | Yes | Yes | Yes |
| Download documents | Own docs only | Controlled | No | No | Controlled |
| Manage facility subscription | No | No | No | Yes | Yes |
| View audit logs | No | Limited | No | Own facility | Yes |

# 5. Product Modules and User Journeys

## 5.1 Module Overview

| Module | Purpose | Core Features |
| --- | --- | --- |
| Public Website | Explain Afyalink, attract professionals and facilities, collect leads. | Home, About, How It Works, Professional CTA, Facility CTA, Contact, FAQs. |
| Authentication & Identity | Secure user accounts and roles. | Registration, login, email verification, password reset, MFA for admins, role permissions. |
| Professional Portal | Receive complete professional applications. | Profile form, credential upload, consent, fee payment, status tracking, replacement requests. |
| Admin Portal | Run Afyalink operations. | Application queues, document review, verification tasks, interview scheduling, scoring, facility management, reports. |
| Verification Workflow | Confirm credential validity with councils and bodies. | Verification request records, evidence notes, source URLs, expiry tracking, status history. |
| Interview Workflow | Assess professionals using structured scorecards. | Scheduling, interviewer assignment, scoring rubric, comments, final recommendation status. |
| Facility Portal | Give paying facilities controlled candidate access. | Subscription, search filters, read-only profiles, appointment booking, recommendation requests. |
| Payments | Collect professional and facility fees. | M-PESA STK Push, manual payment fallback, callbacks, receipts, payment reconciliation. |
| Notifications | Keep users informed. | Email/SMS notifications for submission, payment, review status, interview, facility appointments. |
| Audit & Compliance | Trace every sensitive action. | View logs, exports for compliance team, access alerts, unusual activity detection. |

## 5.2 Professional Journey

1. Professional opens Afyalink and creates an account.

2. Professional verifies email/phone and completes profile details.

3. Professional selects profession and regulatory body.

4. Professional uploads required credentials and identity documents.

5. Professional signs/accepts consent for credential verification and controlled sharing.

6. Professional pays application/interview fee or submits payment reference.

7. Afyalink reviews documents and requests replacements if needed.

8. Afyalink verifies registration/license status with relevant body.

9. Afyalink schedules interview and submits structured marks.

10. Approved professional becomes visible to authorized facilities.

## 5.3 Facility Journey

1. Facility registers and submits facility legitimacy information.

2. Afyalink approves facility account and subscription/payment status.

3. Facility views verified professionals according to its access plan.

4. Facility filters candidates by profession, county, experience, availability, score, and license status.

5. Facility opens read-only candidate profile with dynamic watermark and no download controls.

6. Facility books appointment with Afyalink or requests a recommended shortlist.

7. Afyalink recommends candidate(s) and records decision trail.

# 6. Engineering Architecture

The recommended architecture for Afyalink is a secure modular monolith. This approach gives the speed of a single deployable backend while keeping modules separated enough to split later into services if the product grows.

Figure 1. Suggested Afyalink high-level architecture. The core design keeps documents private, routes all access through the API, and writes all sensitive events to audit logs.

## 6.1 Architecture Layers

| Layer | Responsibility | Strong Engineering Requirements |
| --- | --- | --- |
| Frontend layer | Professional portal, facility portal, admin dashboard, public website. | Type-safe forms, guarded routes, role-based UI, server-side rendering where useful, accessible UI components. |
| API layer | Business logic, access control, workflows, payment callbacks, integrations. | Validation at every boundary, consistent error handling, idempotent payment callbacks, audit logging middleware. |
| Domain modules | Auth, professionals, credentials, verification, interviews, facilities, appointments, payments. | Clear module boundaries, service classes, domain events, test coverage, no direct cross-module table hacks. |
| Data layer | PostgreSQL, Redis, private file storage, backups. | Migrations, indexes, encrypted secrets, backup verification, retention policies. |
| External integrations | M-PESA Daraja, email/SMS, regulatory body portals/APIs, calendar tools. | Retry logic, callback verification, failure queues, admin fallback processes. |
| Observability | Logs, metrics, alerts, audit records, error tracing. | Centralized logs, incident alerts, uptime checks, security event reporting. |

## 6.2 Recommended Architecture Pattern

Modular monolith first: One backend application with clean modules, shared authentication, shared database, and internal services.

Domain-driven modules: Treat professional onboarding, verification, interview, facility access, and payments as separate domains.

Event-driven workflows: Emit events such as ProfessionalSubmitted, PaymentConfirmed, CredentialRejected, VerificationCompleted, InterviewScored, CandidatePublished.

Queue workers: Use background jobs for email/SMS, file scanning, payment reconciliation, report generation, and verification follow-ups.

API-first design: Design internal APIs before UI implementation so the mobile app or partner API can be added later.

Infrastructure as code later: Start with Docker and CI/CD; move to Terraform or Pulumi when production infrastructure matures.

# 7. Recommended Frameworks and Technology Stack

Primary recommendation Use a TypeScript-first stack: Next.js for the web portals, NestJS for the backend API, PostgreSQL for the database, Redis for queues/cache, private S3-compatible object storage for credentials, and M-PESA Daraja for payments. This gives strong engineering structure, type safety, scalable hiring, and clean separation between frontend and backend.

| Area | Recommended Choice | Why This Is Strong for Afyalink |
| --- | --- | --- |
| Frontend | Next.js + React + TypeScript | Strong ecosystem, SEO-friendly public site, fast dashboards, reusable portal components, good support for secure server-side route checks. |
| UI framework | Tailwind CSS + shadcn/ui | Fast, modern, professional UI development with accessible, reusable components and consistent design language. |
| Backend API | NestJS + TypeScript | Enterprise-grade structure, modules, dependency injection, guards, decorators, validation pipes, queues, and clean architecture support. |
| Alternative backend | Laravel | Excellent if the team prefers PHP and wants faster full-stack delivery; strong queues, auth, policies, jobs, and M-PESA integrations. |
| Database | PostgreSQL | Reliable relational database for credential records, verification history, audit logs, payments, and structured reporting. |
| ORM | Prisma or TypeORM | Type-safe database access. Prisma is excellent for developer speed; TypeORM fits NestJS patterns well. |
| Cache / queues | Redis + BullMQ | Background jobs for notifications, verification follow-ups, file scanning, and delayed tasks. |
| File storage | AWS S3, Cloudflare R2, or MinIO | Private object storage with signed URLs, versioning, bucket policies, and future scalability. |
| Authentication | Custom JWT + refresh tokens, or Keycloak/Auth0/Clerk | Supports role-based access, MFA, session control, and enterprise security needs. |
| Payments | Safaricom M-PESA Daraja STK Push | Best local payment fit for Kenya; supports payment prompts and automated callbacks. |
| Email/SMS | Resend/SendGrid + Africa’s Talking/Twilio | Reliable transactional communication for OTPs, application status, interview notifications, and appointment reminders. |
| Deployment | Docker + managed VPS/cloud; later Kubernetes only if needed | Keeps deployments reproducible without overengineering the MVP. |
| CI/CD | GitHub Actions | Automated tests, linting, security checks, migrations, and deployments. |
| Monitoring | Sentry + uptime monitoring + structured logs | Quickly detects errors, failed callbacks, payment issues, and production incidents. |
| Security scanning | OWASP ZAP, npm audit/pnpm audit, Snyk or GitHub Dependabot | Helps detect web vulnerabilities and vulnerable dependencies early. |

## 7.1 Recommended Repository Structure

afyalink/
  apps/
    web/                 # Next.js public site + professional/facility portals
    admin/               # Admin dashboard, can also be route group inside web
    api/                 # NestJS backend API
  packages/
    ui/                  # Shared UI components
    types/               # Shared TypeScript types and DTO contracts
    config/              # ESLint, TypeScript, Tailwind, environment schemas
  infra/
    docker/              # Dockerfiles and compose files
    ci/                  # GitHub Actions workflows
  docs/
    product/             # Product specs and workflows
    security/            # Threat model, policies, access control matrix
    api/                 # OpenAPI specification

## 7.2 Strong Engineering Practices Required

TypeScript strict mode in all frontend and backend applications.

Schema validation using Zod, class-validator, or equivalent at every API boundary.

Database migrations reviewed before production deployment.

All sensitive actions pass through centralized authorization guards.

Separate environments: local, staging, and production.

No production credentials stored in code or committed to Git.

Every uploaded file scanned, type-checked, size-limited, and stored privately.

Every payment callback processed idempotently to avoid duplicate confirmations.

Every sensitive document view logged with user, facility, timestamp, IP, candidate, and action.

# 8. Security, Privacy, and Document Protection

Afyalink should be designed as a sensitive-data platform from the first milestone. Security must not be treated as a later feature because the platform stores identification documents, licenses, academic credentials, interview scores, and facility hiring signals.

## 8.1 Security Baseline

| Security Requirement | Implementation Detail |
| --- | --- |
| Authentication | Email verification, secure password hashing, optional phone OTP, admin MFA, session invalidation after password reset. |
| Authorization | RBAC plus attribute checks: user role, facility subscription, candidate publication status, document type, assigned officer. |
| Document storage | Private bucket only. Files never served from public URLs. Access through API-generated short-lived signed URLs or streaming proxy. |
| Encryption | TLS everywhere, encrypted secrets, database encryption where cloud provider supports it, encrypted backups. |
| Audit logging | Immutable append-style logs for document views, status changes, verification edits, interview marks, payment updates, and admin actions. |
| Input validation | Validate file types, file size, extension, MIME type, form fields, phone numbers, license numbers, and dates. |
| Rate limiting | Protect login, OTP, password reset, document viewer, and search endpoints. |
| Malware scanning | Queue uploaded files for antivirus scan before admin/facility viewing. |
| Least privilege | Staff accounts see only records required by their role; facility users see only authorized published profiles. |
| Backups | Automated daily backups, off-site retention, periodic restore test, audit of backup access. |

## 8.2 Read-Only Document Viewer Design

The facility portal should not expose downloadable PDFs or direct file links. Instead, Afyalink should show documents through a controlled viewer.

Render documents to images or secure PDF viewer pages on the server side, not raw files directly.

Apply dynamic watermark: facility name, user email, timestamp, candidate ID, and access session ID.

Disable download, print, copy, and right-click controls in the viewer interface.

Use short-lived signed access tokens for each viewed document page.

Block indexing and caching of sensitive pages with secure cache headers.

Track every page view in audit logs.

Add facility contractual terms prohibiting screenshots, downloads, redistribution, scraping, and reuse outside the hiring purpose.

Show a visible warning: all views are logged and watermarked.

Screenshot reality check Browser controls can discourage screenshots but cannot fully prevent a user from taking a phone photo or OS-level screenshot. The real control is deterrence plus traceability: dynamic watermarks, legal agreements, audit logs, facility accountability, and limited access windows.

## 8.3 OWASP-Informed Security Controls

| Risk Area | Afyalink Control |
| --- | --- |
| Broken access control | Centralized authorization guards, policy tests, facility subscription checks, object-level access checks for every candidate/document. |
| Security misconfiguration | Environment hardening, disabled debug mode in production, secure headers, restricted CORS, private buckets. |
| Supply chain failures | Dependency scanning, lockfiles, Dependabot/Snyk alerts, approved package policy. |
| Cryptographic failures | TLS, strong password hashing, encrypted secrets, no sensitive data in logs, backup encryption. |
| Injection | ORM parameterization, validation, no raw SQL without review, output encoding. |
| Vulnerable authentication | MFA for admins, rate limits, secure cookies, refresh token rotation, session logout. |
| Logging and monitoring failures | Security event logs, alerting for unusual document access, payment callback failures, repeated login failures. |

# 9. Data Model and Core Database Tables

The data model should preserve history. Avoid overwriting critical verification or interview records without keeping an audit trail.

| Table | Purpose | Important Fields |
| --- | --- | --- |
| users | All login identities. | id, name, email, phone, password_hash, status, email_verified_at, last_login_at. |
| roles | System roles. | id, name, description. |
| user_roles | Role assignments. | user_id, role_id, scope_type, scope_id. |
| professionals | Professional profile. | user_id, profession_id, county, id_number_hash, years_experience, availability, application_status. |
| professional_credentials | Uploaded documents. | professional_id, document_type, file_object_key, original_filename, checksum, review_status, expiry_date. |
| consents | Consent records. | user_id, consent_type, accepted_text_version, accepted_at, ip_address. |
| regulatory_bodies | Supported councils/bodies. | name, profession_category, website_url, verification_method, contact_channel. |
| verification_requests | Verification task records. | professional_id, regulatory_body_id, status, assigned_to, requested_at, due_at. |
| verification_results | Outcome of verification. | request_id, license_status, expiry_date, evidence_reference, verified_by, verified_at. |
| interviews | Interview schedule and status. | professional_id, interviewer_id, scheduled_at, mode, status, completed_at. |
| interview_scorecards | Structured marks. | interview_id, clinical_score, ethics_score, communication_score, experience_score, total_score, recommendation. |
| facilities | Employing institutions. | name, facility_type, county, registration_number, verification_status, subscription_status. |
| facility_users | Facility team members. | facility_id, user_id, role, status. |
| candidate_publications | Who is visible to facilities. | professional_id, publish_status, visibility_level, published_at, unpublished_at. |
| candidate_views | Facility profile/document access. | facility_id, user_id, professional_id, document_id, viewed_at, ip_address, session_id. |
| appointments | Facility appointment requests. | facility_id, requested_by, appointment_type, scheduled_at, status, notes. |
| recommendations | Afyalink shortlist/recommendation records. | facility_id, role_request, recommended_professional_ids, rationale, created_by. |
| payments | Professional and facility payments. | payer_user_id, amount, method, reference, checkout_request_id, mpesa_receipt, status. |
| audit_logs | Security and compliance record. | actor_id, action, entity_type, entity_id, before_json, after_json, ip_address, created_at. |

## 9.1 Key Indexes

users.email unique index.

professionals.user_id unique index.

professionals.profession_id + county + application_status composite index for search.

professional_credentials.professional_id + document_type index.

verification_requests.status + assigned_to index for admin queues.

payments.checkout_request_id and payments.mpesa_receipt unique indexes where available.

candidate_views.facility_id + professional_id + viewed_at index for audit reports.

audit_logs.entity_type + entity_id + created_at index.

## 9.2 Status Design

| Workflow | Recommended Statuses |
| --- | --- |
| Professional application | draft, submitted, payment_pending, payment_confirmed, document_review, needs_correction, verification_pending, interview_pending, approved, rejected, suspended. |
| Credential review | uploaded, scanning, scan_failed, pending_review, accepted, rejected, replacement_required, expired. |
| Verification request | pending, in_progress, verified_valid, verified_invalid, unable_to_verify, expired, escalated. |
| Interview | not_scheduled, scheduled, rescheduled, completed, no_show, cancelled. |
| Facility account | draft, pending_review, approved, rejected, suspended. |
| Subscription/payment | pending, processing, confirmed, failed, reversed, expired. |

# 10. API and Integration Design

The API should be designed around business workflows instead of raw database tables. Every endpoint must validate input, authorize access, and record audit events where sensitive data is affected.

| API Area | Example Endpoints | Notes |
| --- | --- | --- |
| Authentication | POST /auth/register, POST /auth/login, POST /auth/refresh, POST /auth/forgot-password | Rate-limited; secure token handling; MFA for admin roles. |
| Professional profile | GET /me/professional, PATCH /me/professional, POST /professional/submit | Professional can only modify own draft/needs-correction profile. |
| Credential upload | POST /credentials/upload-url, POST /credentials/complete, GET /credentials/:id/view | Use private storage; signed upload/download; virus scanning; audit viewing. |
| Admin applications | GET /admin/applications, GET /admin/applications/:id, PATCH /admin/applications/:id/status | Requires admin permissions; changes audited. |
| Verification | POST /admin/verifications, PATCH /admin/verifications/:id/result | Records verification source, officer, date, and evidence. |
| Interviews | POST /admin/interviews, PATCH /admin/interviews/:id/score | Scorecard locked after submission except controlled amendment. |
| Facilities | POST /facilities/register, GET /facility/candidates, GET /facility/candidates/:id | Requires facility approval and active subscription. |
| Appointments | POST /facility/appointments, PATCH /admin/appointments/:id | Calendar and notification integration later. |
| Payments | POST /payments/mpesa/stk, POST /payments/mpesa/callback | Callback signature validation, idempotency, reconciliation queue. |
| Audit logs | GET /admin/audit-logs | Restricted to super admin/compliance roles. |

## 10.1 M-PESA Daraja Payment Flow

1. Professional selects application/interview fee and enters phone number.

2. Backend creates pending payment record with internal reference and idempotency key.

3. Backend calls M-PESA STK Push endpoint using Daraja credentials.

4. Professional receives phone prompt and enters M-PESA PIN.

5. Daraja sends callback to Afyalink callback endpoint.

6. Backend verifies callback, updates payment status, stores receipt, and emits PaymentConfirmed event.

7. Application status changes from payment_pending to payment_confirmed.

8. Notification is sent to professional and admin queue is updated.

Payment engineering rule Never trust only the frontend after payment. Payment confirmation must come from a verified server-side callback or admin reconciliation process. Callback processing must be idempotent so repeated callbacks cannot duplicate a payment.

## 10.2 Regulatory Body Verification Integration

| Phase | Method | Engineering Detail |
| --- | --- | --- |
| Phase 1 | Manual verification workflow | Admin records verification source, notes, screenshots/evidence references if legally allowed, date, officer, and result. |
| Phase 2 | Public register assisted verification | System stores official lookup URLs and guides officer through required fields; still human-reviewed. |
| Phase 3 | Email/API integration | Where regulatory bodies provide API or formal data-sharing channels, connect through secure integration with logs and retry handling. |
| Phase 4 | Automated expiry monitoring | System alerts professionals and facilities when license expiry approaches or verification becomes stale. |

# 11. Verification, Interview, and Recommendation Workflows

## 11.1 Credential Verification Workflow

1. Professional submits required documents and consent.

2. System checks file type, file size, malware scan status, and required document completeness.

3. Verification officer reviews documents for legibility, consistency, names, dates, and license numbers.

4. Officer selects relevant regulatory body and creates verification request.

5. Officer checks official register, portal, email confirmation, or formal communication channel.

6. Officer records result: valid, invalid, expired, not found, mismatch, or unable to verify.

7. If valid, system marks professional as verification_passed and eligible for interview.

8. If invalid or mismatch, system escalates to senior admin and professional receives correction/rejection communication.

## 11.2 Interview Scorecard

| Score Area | Weight | Example Evaluation Items |
| --- | --- | --- |
| Clinical/professional competence | 30% | Role-specific technical questions, standard operating procedures, safety awareness, documentation accuracy. |
| Ethics and professionalism | 20% | Confidentiality, patient dignity, regulatory awareness, accountability, honesty. |
| Communication | 15% | Patient communication, team communication, escalation clarity, written communication. |
| Experience and role fit | 15% | Relevant work history, facility type exposure, specialty experience, availability. |
| Scenario judgment | 15% | Handling emergencies, conflicts, low-resource settings, reporting incidents. |
| Afyalink risk flags | 5% | Credential mismatch, unexplained gaps, poor references, repeated no-shows, incomplete records. |

Recommended scoring bands: 85-100 = highly recommended, 70-84 = recommended, 55-69 = conditional recommendation, below 55 = not recommended without further review.

## 11.3 Facility Recommendation Workflow

1. Facility submits staffing need: profession, location, duration, shift pattern, experience level, specialty, urgency, and budget range.

2. Afyalink filters eligible professionals by verified status, active license, location, availability, experience, and interview score.

3. System generates internal shortlist.

4. Afyalink staff reviews shortlist and adds recommendation rationale.

5. Facility receives read-only shortlist and books appointment if needed.

6. Facility decision is recorded for future matching intelligence.

# 12. Milestone Roadmap

| Milestone | Goal | Key Deliverables | Estimated Duration |
| --- | --- | --- | --- |
| Milestone 1 | Professional application and credential intake MVP. | Public site, auth, professional profile, credential upload, consent, payment reference/M-PESA foundation, admin review, status tracking. | 3-5 weeks |
| Milestone 2 | Verification and interview workflow. | Regulatory verification tasks, interview scheduling, scorecards, approval/rejection, notification improvements. | 3-4 weeks |
| Milestone 3 | Facility portal and controlled candidate access. | Facility onboarding, subscription, candidate search, read-only profile viewer, watermarks, appointment booking. | 4-6 weeks |
| Milestone 4 | Recommendation and matching engine. | Role requests, shortlist generation, recommendation rationale, facility reports, matching analytics. | 3-5 weeks |
| Milestone 5 | Compliance, scale, and automation. | Advanced audit reports, automated expiry reminders, regulatory integrations, data retention workflows, dashboards. | Ongoing |
| Milestone 6 | Mobile and partner expansion. | Professional mobile app, facility mobile app, partner API, multi-country regulatory support. | Later |

# 13. Milestone 1 Detailed Build Plan

Milestone 1 objective Build the first working Afyalink MVP where a healthcare professional registers, completes a profile, uploads credentials, gives consent, pays/submits payment reference, submits an application, and Afyalink admin reviews documents and marks the application ready for verification/interview.

## 13.1 Milestone 1 Scope

| Feature | Must Have in Milestone 1 | Can Wait Until Later |
| --- | --- | --- |
| Public website | Home, About, How It Works, Professionals CTA, Facilities CTA, Contact. | Blog, advanced SEO, testimonials, multilingual content. |
| Authentication | Professional and admin login/register, email verification, password reset. | Facility login, SSO, social login. |
| Professional profile | Complete application form with profession, regulatory body, license number, experience, location, availability. | AI CV parser, auto-complete from council APIs. |
| Credential upload | CV, ID/passport, license, academic certificates, work letters; private storage. | Advanced OCR, automated document classification. |
| Consent | Mandatory consent checkbox/version record before submission. | Digital signature integration. |
| Payment | Manual payment reference or M-PESA STK Push foundation. | Subscription billing, refunds, wallet, invoices. |
| Admin dashboard | Application list, profile view, document review, payment status, application status update, internal notes. | Advanced analytics, staff productivity reports. |
| Notifications | Basic email/SMS for submission, payment confirmation, needs correction. | Full workflow automation and campaigns. |
| Audit logs | Log application submission, document view, status changes, payment confirmation. | Advanced anomaly detection. |

## 13.2 Milestone 1 User Stories

| User Story | Acceptance Criteria |
| --- | --- |
| As a professional, I can create an account. | Registration works, email is unique, password is hashed, user receives verification email. |
| As a professional, I can complete my profile. | Required fields are validated; draft is saved; profile can be edited before submission. |
| As a professional, I can upload credentials. | Only allowed file types/sizes are accepted; files are stored privately; upload status is visible. |
| As a professional, I can consent to verification. | Consent text version, timestamp, user ID, and IP are stored. Submission blocked without consent. |
| As a professional, I can submit payment reference. | Reference is stored; admin can mark confirmed; application status updates. |
| As an admin, I can view submitted applications. | Admin sees list with filters: status, profession, date, payment, document review. |
| As an admin, I can review documents. | Admin can mark accepted, rejected, or replacement required and add comments. |
| As an admin, I can update application status. | Status changes are validated and audited; professional sees new status. |
| As the system owner, I can see audit logs. | Audit table captures key actions with actor, action, entity, IP, timestamp. |

## 13.3 Milestone 1 Sprint Plan

| Week | Engineering Work | Output |
| --- | --- | --- |
| Week 1 | Finalize requirements, create UI wireframes, set up repo, database, auth, environments, CI pipeline. | Running project skeleton with login/register and database migrations. |
| Week 2 | Build professional profile form, document type rules, credential upload, private storage integration. | Professional can save profile and upload required credentials. |
| Week 3 | Build consent capture, application submission, payment reference/M-PESA foundation, notification templates. | Professional can submit complete application and payment reference. |
| Week 4 | Build admin dashboard, application list, document review, payment confirmation, internal notes, status management. | Admin can review applications and update statuses. |
| Week 5 | Testing, security hardening, audit logs, deployment to staging, bug fixing, demo preparation. | Working MVP deployed to staging/production-ready pilot environment. |

## 13.4 Milestone 1 Screen List

Public: Home, About, How It Works, For Professionals, For Facilities, Contact.

Auth: Register, Login, Forgot Password, Verify Email.

Professional: Dashboard, Profile Form, Credential Upload, Consent, Payment, Application Status.

Admin: Dashboard, Application List, Application Detail, Document Viewer, Payment Review, Status Change, Internal Notes, Audit Log List.

## 13.5 Milestone 1 Definition of Done

A professional can complete and submit an application without developer intervention.

All required documents are stored privately and are not accessible through public URLs.

Admin can open an application, review documents, confirm payment, and change application status.

Professional can see status updates from their dashboard.

At least critical paths have automated tests: registration, profile save, upload, submission, admin review.

Audit logs exist for sensitive actions.

Deployment has staging and production environment variables separated.

Basic backup policy is configured.

No secrets are committed to the repository.

MVP demo can show a nurse/clinical officer application from registration to admin-ready-for-verification status.

## 13.6 Milestone 1 Data to Seed

| Seed Data | Examples |
| --- | --- |
| Professions | Nurse, Clinical Officer, Medical Officer, Dentist, Pharmacist, Lab Technologist, Physiotherapist, Nutritionist, Public Health Officer. |
| Document types | National ID/Passport, CV, Professional License, Academic Certificate, Work Experience Letter, CPD/Retention Document. |
| Regulatory bodies | KMPDC, Nursing Council of Kenya, Clinical Officers Council, Pharmacy and Poisons Board, other phased councils. |
| Application statuses | draft, submitted, payment_pending, payment_confirmed, document_review, needs_correction, verification_pending, interview_pending. |
| Admin roles | Super Admin, Verification Officer, Interviewer, Support Agent. |

# 14. Delivery Team, Testing, Risks, and References

## 14.1 Recommended Delivery Team

| Role | Responsibility | Minimum Need |
| --- | --- | --- |
| Product owner / founder | Owns requirements, regulatory relationships, pricing, approvals, and demo acceptance. | Part-time daily availability. |
| UI/UX designer | Wireframes, user flows, visual design system, professional/facility dashboard UX. | 1 designer during first 2 weeks, then support. |
| Frontend engineer | Next.js portals, forms, document viewer, dashboard interfaces. | 1 strong engineer. |
| Backend engineer | NestJS API, database, auth, workflows, payments, file storage, audit logs. | 1 strong engineer. |
| QA/tester | Test cases, regression testing, browser testing, acceptance testing. | Part-time initially. |
| Security/compliance advisor | Data protection, access control, policy review, legal terms, risk register. | Part-time advisory. |

## 14.2 Testing Plan

| Test Type | What to Test |
| --- | --- |
| Unit tests | Validation services, status transition rules, payment callback parser, permission guards. |
| Integration tests | Registration + profile + upload + submission; admin review + status update; payment callback + application update. |
| End-to-end tests | Professional application journey and admin review journey using Playwright or Cypress. |
| Security tests | Unauthorized document access, facility trying to view unpublished candidate, IDOR checks, brute-force login limits. |
| File tests | Invalid file type, oversized upload, duplicate files, private URL checks, malware scan queue. |
| Payment tests | Successful callback, failed callback, duplicate callback, delayed callback, manual reconciliation. |
| Usability tests | Can a professional complete the form without support? Can an admin review quickly? |

## 14.3 Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Regulatory verification is slow or manual. | Application backlog, delayed candidate approval. | Use phased manual workflows, SLAs, evidence notes, verification queues, and clear candidate status messaging. |
| Facilities attempt screenshots or misuse data. | Privacy breach and reputational damage. | Dynamic watermarks, audit logs, facility contracts, restricted access, legal terms, and alerting for unusual activity. |
| Payment callbacks fail or duplicate. | Incorrect payment status. | Idempotency keys, reconciliation dashboard, retry queue, manual override with audit. |
| Uploaded files contain malware or sensitive hidden metadata. | Security compromise. | Antivirus scanning, file conversion, metadata stripping, and private quarantine until scan passes. |
| Admins accidentally approve invalid credentials. | Trust failure and potential liability. | Two-step approval for high-risk cases, evidence requirements, supervisor review, status history. |
| Data protection non-compliance. | Legal penalties and loss of trust. | ODPC assessment, data map, consent records, privacy policy, retention rules, breach response plan. |
| Overbuilding before validation. | Slow launch and wasted cost. | Deliver Milestone 1 first, then validate professional onboarding and facility interest before advanced automation. |

## 14.4 Immediate Next Steps

1. Finalize Afyalink business policy: professional fee, facility pricing, refund policy, and verification disclaimers.

2. Approve the Milestone 1 scope in this document.

3. Create wireframes for professional application and admin review screens.

4. Set up Git repository, environments, database, and initial CI pipeline.

5. Build authentication, profile form, credential upload, and admin review workflow.

6. Pilot with 10-20 professionals and 2-3 trusted facilities before scaling.

## 14.5 Reference Sources

Kenya Health Professions Oversight Authority (KHPOA): https://khpoa.go.ke/

Kenya Ministry of Health - SAGA's, Regulatory Bodies and Councils: https://www.health.go.ke/sagas-regulatory-bodies-and-councils

Office of the Data Protection Commissioner (ODPC): https://www.odpc.go.ke/

ODPC Data Handler Registration Portal: https://dataportal.odpc.go.ke/

Safaricom Daraja Developer Portal: https://developer.safaricom.co.ke/

OWASP Top 10 Web Application Security Risks: https://owasp.org/www-project-top-ten/

KMPDC Registers for Practitioners: https://kmpdc.go.ke/registers-practitioners-php/

Clinical Officers Council License Status: https://portal.clinicalofficerscouncil.org/LicenseStatus

Nursing Council of Kenya Online Services Portal: https://osp.nckenya.com/